## Live Bug Reporting Sheet
SR | POINTS | TYPE | STATUS | REMARKS | Heptanesia Remarks | Live Status
1 | Bug Title: Update Official Email Domain for TPO, Management, and Faculty Description: Currently, the system validates or uses email IDs with the @silveroak.ac.in domain for TPO, Management, and Faculty users. Expected Behavior: The official email domain should be updated to @silveroakuni.ac.in. All validations, user creation, login, and email-related functionality should accept and use @silveroakuni.ac.in instead of @silveroak.ac.in. | BUG | UAT | Accepted |  | Done
2 | Bug Title: Rejected Students Should Not Be Added to Posting Type Description: When a student enrolls, the record is displayed in the Student Management module. However, if the student is rejected from Student Management, the student's details are still being added to the Posting Type section. Expected Behavior: If a student is rejected in Student Management, the student's record should not be added to or displayed in the Posting Type section. Actual Behavior: Rejected students are being added to the Posting Type section despite their rejection status. | BUG | UAT | Accepted |  | Done
3 | Bug Title: Verify Option Not Available After Student Rejection Description: When a student is rejected in the Student Management module, the system does not provide an option to verify the student again. Expected Behavior: After a student is rejected, an authorized user should have the option to re-verify or change the student's status if required. Actual Behavior: Once a student is rejected, the Verify option is no longer available, preventing the student from being verified again. | BUG | UAT | Accepted |  | Done
4 | Bug Title: Posting Type Policy Acceptance Not Enforced Before Application Description: Currently, when a student shows interest in a specific Posting Type, the policy defined for that Posting Type in the TPO Admin Profile is not displayed. Expected Behavior: When a student clicks Show Interest or Apply for a Posting Type, the system should display the policy/terms configured by the TPO Admin for that specific Posting Type. The student must be required to read and accept the policy by checking an "I Agree" checkbox. The Apply button should remain disabled until the policy has been accepted. Once the student accepts the policy, the Apply button should become enabled, allowing the application to proceed. Configuration Source: Policy content should be fetched from the TPO Admin Profile → Policy Repository. configured for the respective program/posting type. | BUG | UAT | Accepted |  | Done
5 | Bug Title: Posting Visibility Is Not Restricted to Students Enrolled in the Posting Type Bug Description: Currently, when a posting is published under a specific Posting Type, it is visible to all students who have access to the associated Program. Expected Behavior: Students should first enroll (show interest) in the Posting Type. Only students who are enrolled in that Posting Type should be able to view the postings under it. Only enrolled students should be allowed to apply for those postings. Current Behavior: All students with access to the Program(Posting type) can view and apply for postings under the Posting Type, even if they have not enrolled (shown interest) in that Posting Type. | BUG | UAT | Accepted |  | Done
6 | Bug Title: Simplify Create Event by inheriting Posting Type configuration Bug Description: The Create Event form require the following selections: Posting Type (Dropdown) Company (Filtered based on the selected Posting Type) Linked Posting (Filtered based on the selected Company) The flow should be: Select Posting Type. The Company dropdown should automatically display only the companies linked to that Posting Type. After selecting a Company, the Linked Posting dropdown should display only the linked postings of that company. All other configurations (Institute, Program, Branch, Semester, etc.) should be automatically inherited from the selected Posting Type. There should be no need to configure these fields again while creating an Event. | BUG | UAT | Accepted |  | Done
7 | Title: Create Event – Allow Multiple Role Selection in Linked Posting Bug / Enhancement Description: Currently, the Linked Posting field in Create Event allows only a single role (posting) to be selected. The system should support multiple role selection, so that one event can be linked to multiple postings/roles within the selected company. Expected Behavior: The Linked Posting field should be a multi-select dropdown. Users should be able to select one or more linked postings (roles). The event should be associated with all the selected roles. Students assigned to any of the selected linked postings should be able to view the event (based on the existing visibility rules). | BUG | UAT | Accepted |  | Done
8 | Bug Title: Placed Students Database Not Fetching Released Offers & NOC Status Label Required Issue 1: In the Student Management → Placed Students Database, no records are being fetched for students whose offers have been released. The database should automatically display all students with Released Offers. Issue 2 (Enhancement): For every fetched student record, add an NOC Status label to indicate whether the student has completed the NOC process after the offer release. Suggested NOC Status Values: NOC Issued – NOC has been generated/issued. NOC Pending – NOC has not yet been issued. This will help the Training & Placement Cell easily track the NOC status of placed students after the offer release. Path: Student Management → Selection Database → Placed Students Database | BUG | UAT | Accepted |  | Done
9 | Bug Title: Company and Recruiter Should Be Auto-Created After NOC Approval for New Company Description: When a student submits an NOC request with a new company and the request is approved by the TPO, the company is added to the company database. However, the corresponding recruiter is not created automatically. Expected Behavior: If the company is new and the TPO approves the NOC, then: The company should be automatically added to the company database. The recruiter details should also be automatically created and linked to the newly added company. | Bug | UAT | Accepted |  | Done
10 | Title: No Due Attachment Not Visible Bug Description: The attachment uploaded in the No Due section is not visible after submission. Although the attachment appears to be uploaded successfully, it is not displayed when viewing the No Due record. Expected Behavior: The uploaded No Due attachment should be visible and accessible for viewing/downloading from the No Due record. | Bug | UAT | Accepted |  | Done
11 | Bug Description: The Notification module crashes with the following React runtime error when accessed: Minified React error #130; visit https://reactjs.org/docs/error-decoder.html?invariant=130&args[]=undefined&args[]= | Bug | UAT | Accepted |  | Done
12 | Title: Missing Profile Photo Update Option in Student Dashboard Bug Description: After logging into the Student Dashboard, there is no option available for students to upload, change, or update their profile photo. | Bug | UAT | Accepted |  | Done
13 | Bug Title: Create Event – Target Audience displays all students from the selected Posting Type instead of filtering based on the selected Company and Job Profile(s) Description: While creating an event, the Target Audience should be automatically inherited based on the selected Posting Type → Company → Job Profile (Role) hierarchy | Bug | UAT | Accepted |  | Done
14 | Bug Title: Super Admin – ERP Fetched Fields Should Be Read-Only Description: In Super Admin → Add User, the fields fetched from the ERP are editable. Expected Result: ERP-fetched fields should be read-only (non-editable). | Bug | UAT | Accepted |  | Done
15 | Bug Title: Project Date Validation in Student Profile Description: In the Student Profile → Project section: The Project Date should be mandatory and must not allow a future date (it should be today's date or any past date only). Proper validation should be implemented for Start Date and End Date: Start Date cannot be after the End Date. End Date cannot be before the Start Date. Invalid date combinations should display appropriate validation messages. | Bug | UAT | Accepted |  | Done
16 | Bug: Student Portfolio is not displaying all captured fields. In (TPO ADMIN) Description: All the fields collected from the student should be displayed in the Student Portfolio. Currently, the Project Start Date and Project End Date are not visible in the Project section, even though these fields are captured during data entry. | Bug | UAT | Accepted |  | Done
17 | 1.Bug: Certification Date Validation Missing 2.Bug: View Issue Description: In the Certification section, students should only be allowed to add certifications with a date that is today or earlier. Currently, the system also allows future certification dates, which should not be permitted. Expected Result: The Certification Date should not accept any future date. Only today's date or any past date should be allowed. | Bug | UAT | Accepted |  | Done
18 | Bug: Attachment Preview Not Working & File Type Validation Description: Across most modules, attachments are being uploaded successfully but are not visible/viewable after upload. Additionally, the system currently allows multiple file types for attachments.the system should accept PDF files only. Currently, multiple file formats are allowed, leading to inconsistency. | Bug | UAT | Accepted |  | Done
19 | Bug: TPO Admin Review – Approved Faculty Name Not Displayed Description: When the TPO Admin reviews a student's request, the system currently displays only the approval date and time. The name of the faculty coordinator who approved the request is not shown. Expected Behavior: Along with the approval date and time, the system should also display the name of the faculty member who approved the request so that the approval history is complete and easily traceable. | Bug | UAT | Accepted |  | Done
20 | Bug: Student – Opportunities – Minimum Stipend Filter Not Working Description: On the Student → Opportunities page, the Minimum Stipend filter is not functioning correctly. When a minimum stipend value is selected or entered, the opportunity list does not filter accordingly and displays incorrect or all records. Expected Result: Only opportunities with a stipend greater than or equal to the selected Minimum Stipend should be displayed. Actual Result: The Minimum Stipend filter has no effect, and the displayed opportunities are not filtered based on the selected stipend value. | Bug | UAT | Accepted |  | Done
21 | Create Event – Dropdown Search Consistency Issue The Company dropdown supports a searchable dropdown, allowing users to quickly find a company by typing its name. However, the Event Type and Posting Type dropdowns do not provide the same search functionality. | Bug | UAT | Accepted |  | Done
22 | Unable to Delete Some Posting Types from Masters – "Referenced Record Does Not Exist" Error | Bug | UAT | Accepted |  | Done
23 | Unable to Add Multiple Institutes, Courses, Branches, and Semester Mapping Missing While Creating Manual Announcement Description: While creating an announcement, the system does not allow selecting multiple Institutes, Courses, and Branches. Additionally, the Semester field is missing. The announcement creation flow should follow a hierarchical mapping: Institute → Course → Branch → Semester The available semesters should be filtered based on the selected branch/course to prevent cross-selection. For example: B.Tech → 4th Semester BCA → 2nd Semester The system should not allow unrelated combinations (e.g., B.Tech with BCA semesters), ensuring announcements are targeted only to the appropriate student group. | Bug | UAT | Accepted |  | Done
24 | There is no option to republish an archived announcement. The system should provide a Publish/Republish option for archived announcements so they can be made active again whenever required. | Bug | UAT | Accepted |  | Done
25 | TPO ADMIN -> Masters- NOC Template Issue: Company Placeholders Not Working in NOC Template While issuing the NOC, the Recruiter Name, Designation, and Company Name are not displayed after the "To," section. Example:- To, Recipient Name Manager – HR / Training Team Company Name | Bug | UAT | Accepted |  | Done
26 | TPO Admin:- Bug: Offer & Joining Management → Offer Records Only 20 records are displayed in the Offer Records list. Pagination is missing, so users cannot navigate to view the remaining records. | Bug | UAT | Accepted |  | Done
27 | Issue: Posting Type Not Filtered While Applying for NOC While applying for an NOC, all posting types are displayed. Expected Behavior: Only the posting types in which the student is enrolled or has shown interest should be displayed while applying for the NOC. | Bug | UAT
28 | Bug: Mobile Number & Pin Code Validation Missing in NOC Application Module: Student → Apply for NOC → Request No Objection Certificate Screen: Step 2 of 4 – Capture Company and Offer Details Issue: Validation is missing for the Mobile Number and Pin Code fields. The system currently accepts invalid or incorrect values. | Bug | UAT | Accepted |  | Done
29 | Bug: State & City Filter Not Working Module: Student → Apply for NOC → Request No Objection Certificate ( in University& Self both Placement Source) Screen: Location form Step 2 – Capture Company and Offer Details Issue: The State and City dropdown filters are not working as expected. Selecting a state does not filter or populate the corresponding city list. | Bug
30 | Bug: Unable to Load Offers Due to Filter Validation Error Module: TPO Admin->Offer & Joining Management Issue: While applying filters in the Offer & Joining Management section, the system displays the following error: Error: "Unable to load offers One or more fields have validation errors." As a result, the offers are not loaded. | Bug | UAT | Accepted |  | Done
31 | Bug: Student List Not Loading During Panel Assignment Module: TPO Admin → Events & Drives → Panel Assignment Issue: While assigning a panel in the Events & Drives module, the student list is not displayed, making it impossible to assign students to the panel. | Bug | UAT | Accepted |  | Done
32 | The Program Specific Policy is displayed only occasionally. Most of the time, the system bypasses the policy and allows users to proceed without showing or enforcing it. | Bug | UAT | Accepted |  | Done
33 | Module: TPO Admin-> Employer Management → Create Company Bug : Company Name Auto-Suggestion to Prevent Duplicate Entries Current Issue: While creating a new company, users can enter a company name that already exists in the Company Master, resulting in duplicate company records. Suggested Enhancement: As the user types in the Company Name field, display auto-suggestions of existing company names from the Company Master. If the entered company name matches or closely resembles an existing company (case-insensitive and ignoring extra spaces), prompt the user to select the existing company instead of creating a new one. Display a message such as: "A similar company already exists. Please select it from the list." If no matching company is found, allow the user to proceed with creating a new company. | Bug | UAT | Accepted |  | Done
34 | Issue: In the Faculty Coordinator Profile → My Program section, records are not being filtered correctly. Common records are being displayed instead of only the relevant program records. | Bug
35 | Issue: Posting Type Label Display in All Postings Description: In the TPO Admin → Postings → All Postings page, the Type column is currently displaying "Stipend Internship" for all records, regardless of the actual posting type. Expected Behavior: Rename the table header from "Type" to "Posting Type". Display the actual Posting Type assigned during the creation of each posting Each record should show its respective posting type instead of displaying "Stipend Internship" for all records. | Bug | UAT | Accepted |  | Done
36 | Issue: In Faculty Coordinator → Department Students → View, the Student Portfolio is not being displayed. Currently, only the Profile information is visible. | Bug

## FILTER COUNTER EXPORT
TPO ADMIN
Interest Lists | Add | Remove
Filters | Academic year filter | department dropdown | Tpo Admin- | TPO Admin Dashboard | Generate Lists->Interest Lists
Institute and course and branch Semester dropdown
date range
Student | Add | Remove
Filters | Academic year filter | department dropdown | Tpo Admin- | TPO Admin Dashboard | Generate Lists->Interest Lists
Institute and course and branch Semester dropdown
date range
Company | Add | Remove
Filters | Institute and course and branch dropdown | department dropdown | Tpo Admin- | Student | Student Management->all students section
Company dropdown
Semester
date range
Export data | name, Mo.No, Gender ,Email, enrollment , Institute ,Course,Branch,Semester ,Cpi ,12th,10th ,Backlog,Academic Year(From ERP) , student project count, student instership count, status, resume link
Filter | Academic year filter |  | Tpo Admin- | Student | Student Management->Verification section
Create Rule | institute and course and branch dropdown | Eligibility Branches | Tpo Admin- | Student | Student Management->Eligibility rules section
Add custom Branch
Filter | institute and course and branch dropdown | department dropdown | Tpo Admin- | Student | Student Management->Portfolio section
Status Dropdown
Average Projects count
Export data |  | Remove Export Functionality
Filter | Institute and course and branch dropdown | department dropdown | Tpo Admin- | Student | Student Management->Selection Data section
| Academic Year | All Batches
Export data | name, Mo.No, Gender ,Email, enrollment , Institute ,Course,Branch,Semester ,Cpi ,12th,10th ,Backlog,Academic Year (from ERP),status,joining date ,Company name ,role,selection date ,NOC status | Remove PDF And Print Option
Finalized Count
Tab | Change the Placement Title with Placements/Internships | Remove Internship Tab section | Tpo Admin- | Student | Student Management
Company | Add | Remove
Filter | Sector/Industry Dropdown |  | Tpo Admin- | Companies | Companies->Employer Management section
date range
Export | Add Export Functionality |  | Tpo Admin- | Companies | Companies->Employer Management section
Company Name ,Industry ,Address ,Website ,Recruiter Name,Email,Contact No.,Designation , Classification, Status (Note-1 Company have Multiple recruiters also , so export data accordingly)
Counter (Company Tab) | Inactive Counter | Preferred & Blacklisted
Counter (Recruiter Tab) | Reject Counter
Posting | Add | Remove
Filter | Posting type | All types dropdown | Tpo Admin- | Posting | Posting ->Posting Operations section
| institute and course and branch dropdown | draft counter dropdown
date range
Export data | Add Export Functionality
Company Name, Academic Year(Masters), Bond Details, Minimum CGPA, Maximum Backlogs, Application Start Date, Application End Date, Posting Type, Role Name, Package Rang, Stipend Range, Status
Applications | Add | Remove
Filter | institute and course and branch dropdown |  | Tpo Admin- | Applications | Applications->Applications Management section
All Posting type - dropdown values should be merge with acadmic year (Ex. Posting type - Acadmic Year)
company dropdown
date range
Export data | Add Resume Link Option
Counter | Applied Counter | Interview Counter
Filter | institute and course and branch dropdown | All Branches | Tpo Admin- | Applications | Applications->Application Pipeline section
date range
offer & Joining Management | Add | Remove
Filter | institute and course and branch dropdown |  | Tpo Admin- | offer & Joining Management | offer & Joining Management section
date range
Search option box not showing properly (BOX SIZE)
Counter | Add Rejected by student counter box
NOC Management | Add | Remove
Counter | Pending Faculty Approval Counter | Approve Counter | Tpo Admin- | NOC Management | NOC Management section
Filter | institute and course and branch dropdown | All Types
| Posting type | All Status Dropdown -> remove Approve
Academic Year
| date range | Ready to Issued Tab remove
Tab | Add Tabs (Pending by Faculty, Pending By TPO, Issued, Rejected, Complition Certificate, All Requets)
Events & Drives | Add | Remove
Counter | Ongoing,Cancelled |  | Tpo Admin- | Events & Drives | Events & Drives
Filter | date range
Academic Year
institute and course and branch dropdown
Buttons | Attendance Export Button, Attendance Import Button, Rename Cancel button to Event Cancel Button (Same in Popup Box also)
Export | Event Name, Company Name,Event Date, Venue, Event Time, Event Status, Panel Name, Panel Room, Panel Start Time, Panel End Time, Recruiters, Students (Registered Student count), present count, Event Type, Faculty Coordinators
Export & Import | Mark Attendance Export & Import Functionality |  | Tpo Admin- | Events & Drives | Mark Attendance
Announcements | Add | Remove
Filter | date range |  | Tpo Admin- | Announcements | Announcements
institute and course and branch dropdown
Circulars | Add | Remove
Circulars | N/A | N/A | Tpo Admin- | Circulars | Circulars
No Dues Management | Add | Remove
Counters | Return, Reject Count | Issued Count | Tpo Admin- | No Dues Management | No Dues Management
Filter | institute and course and branch dropdown | All Status dropdown - remove issued
Passing Year
Policy Repository | Add | Remove
Filter |  | Remove Filter tabs | Tpo Admin- | Policy Repository | Policy Repository
Faculty Coordinator :
Dashboard | Add | Remove
Counters | Total Offer Released |  | Faculty Coordinator-> | Faculty Coordinator Dashbord | Faculty Coordinator Dashbord
Update title from "Placed Students" to "Accepted"
Join Counter (Same as Offer & Joining - Join Counter)
Department Students | Add | Remove
Filters | Instittue, Courses,Branch (ERP), date range (Required) | All Branch, All Institiue | Faculty Coordinator-> | Department Students-> | Student Directory
Label | Enrollment No | Roll no
Export
My Programs | Add | Remove
Export | Change title From Registered On to Instested On Date
Gender
Data Listing | Change title from Source to Status
NOC Approvals | Add | Remove
Counters | Rejeted Count by Department |  | Faculty Coordinator-> | NOC Approvals
Rejeted Count by Tpo
Approved By TPO
Filters | Date Range
academic Year(Source:-Masters)
Posting Type
Table Column | If Issued( NOC Number) |  | Faculty Coordinator-> | NOC Approvals | History->Reviewed Requests
Export | Student Name, enrollmentno, Institute,Course,Branch, Semester ,Posting type, Company Name,Technology / Domain ,Stipend,Status, Offer Letter Link,NOC Certificate Number, NOC Certificate Link, Completion Certficate Link
Offers/ Joining | Add | Remove
Counter | Pending, Rejected | Blocked, Joined | Faculty Coordinator-> | Offers/ Joining | Offer & Joining Status
Date Range
Filter | academic Year(Source:-Masters)
Posting type
All Status dropdown (Option:- Rejected by Students)
Export | Student Name, Enrollment no, Institute,Course,Branch, Semester ,Posting type, Company Name,Role,Stipend,Acceptance Status,joining status
Department Events | Add | Remove
Filter | Search box
Student :
My Applications | Add | Remove
Tab |  | Internship Tab | Student -> | My Applications | Internship
Filter | Posting Type (Single Selection) |  | Student -> | My Applications
NOC Requests | Add | Remove
Filter | Posting Type |  | Student -> | NOC Requests
My Events & Drives | Add | Remove
Filter | Search |  | Student -> | My Events & Drives
Announcements | Add | Remove
Filter | Search |  | Student -> | Announcements
Super Admin:
Security & Access Control (Audit Logs) | Add | Remove
Filter | All user dropdown add other user role options (Like, TPO Admin, Faculty) | Print & PDF | Super admin -> | Security & Access Control | (Audit Logs)

## NEW REPORTS
PLACEMENT COUNT REPORT
Sr | POSTING TYPE (Muplti Selection) | ACADMIC YEAR DATA (FROM POSTING TYPE MODULE) | INSTITUTE/COLLEGE | PROGRAM/COURSE | BRANCH/SPECIALIZATION | SEM/YEAR | TOTAL NO OF STUDENTS | INTERESTED / REGISTERED STUDENTS | NOT INTERESTED STUDENTS | ELIGIBLE STUDENTS (CPI minimum 6.5 CGPA) | COMPANIES PARTICIPATED | NOC COUNT | COMPLETION CERTIFICATE COUNT | HIGHEST PACKAGE | AVERAGE PACKAGE | MEDIAN PACKAGE | LOWEST PACKAGE | Accept Offer (Offer & Joining Module) | Reject Offer (Offer & Joining Module) | Pending Offer (Offer & Joining Module)
1 | FINAL PLACEMENT 26-27 (Multi Selection) | 26-27 | COT | B.TECH | CE | 7 | 3000 | 1500 | 1500 | 1000 | 10 | 100 | 40 | 6 LPA | 2.5 LPA | 3 LPA | 2 LPA | 10 | 2 | 6
2 | FINAL PLACEMENT 26-27 (Multi Selection) | 26-27 | COT | B.TECH | IT | 6 | 4000 | 2000 | 2000 | 1000 | 10 | 100 | 40 | 6 LPA | 2.5 LPA | 3 LPA | 2 LPA | 10 | 3 | 5
PLACEMENT DATA LISTING & EXPORT REPORT
Sr | POSTING TYPE (Muplti Selection) | ACADMIC YEAR DATA (FROM POSTING TYPE MODULE) | ENROLLMENT NO | STUDENT NAME | INSTITUTE/COLLEGE | PROGRAM/COURSE | BRANCH/SPECIALIZATION | SEM/YEAR | CONTACT NO | EMAIL ID | COMPANY NAME | DESIGNATION | PACKAGE | NOC STATUS | OFFER LETTER LINK | Completion Letter (link) | GENDER | Offer Status (Offer & Joining Module)
1 | FINAL PLACEMENT 26-27 | 26-27 | 20205000301245 | BHOOMI K PARMAR | COT | B.TECH | CE | 7 | 9898989898 | BHM@GMAIL.COM | TCS | DEVELOPER | 6 LPA | YES | ABC |  | FEMALE | Accept
2 | FINAL PLACEMENT 26-27 | 26-27 | 20205000302234 | RAJ SHARMA | COT | B.TECH | IT | 6 | 7878787878 | RAJ@GMAIL.COM | TATA | DEVELOPER | 10 LPA | YES | ABC |  | MALE | Accept
INTERNSHIP / NOC DATA COUNT REPORT
Sr | POSTING TYPE (Muplti Selection) | ACADMIC YEAR DATA (FROM POSTING TYPE MODULE) | INSTITUTE/COLLEGE | PROGRAM/COURSE | BRANCH/SPECIALIZATION | SEM/YEAR | TOTAL NO OF STUDENTS | NOC COUNT | NOC ACCEPT | NOC REJECT | TOTAL NO OF STUDENTS - NOC COUNT | University Placement Drive | Self-Sourced / Off-Campus | Source :- NOC Request Highest Stipend | Source :- NOC Request Average Stipend | Completion Certificate Count | company count
1 | FINAL PLACEMENT 26-27 | 26-27 | COT | M.TEHC | ME | 5 | 3000 | 2000 | 2000 | 0 | 1000 | 1500 | 500 | 5000 | 2000 | 5 | 2
2 | FINAL PLACEMENT 26-27 | 26-27 | COT | M.TEHC | CSE | 4 | 2000 | 1000 | 1000 | 0 | 1000 | 500 | 500 | 2000 | 2000 | 6 | 3
INTERNSHIP / NOC DATA DATA LISTING & EXPORT REPORT
Sr | POSTING TYPE (Muplti Selection) | ACADMIC YEAR DATA (FROM POSTING TYPE MODULE) | NOC Number | ENROLLMENT NO | STUDENT NAME | INSTITUTE/COLLEGE | PROGRAM/COURSE | BRANCH/SPECIALIZATION | SEM/YEAR | Student CONTACT NO | EMAIL ID | COMPANY NAME | Role / Position Title | STIPEND | INTERNSHIP START DATE | INTERNSHIP END DATE | INTERNSHIP TYPE (University Placement Drive & Self-Sourced / Off-Campus) | NOC CERTIFICATE LINK | INTERNSHIP OFFER LETTER LINK | INTERNSHIP COMPLETION CERTIFICATE LINK | Source : NOC REQUEST / NOC REGIESTER- RECRUITER COMPANY PERSON NAME | Recruiter Contact Details | Recruiter Email ID | Recruiter Designation | Student Photo (link) | INTERNSHIP + PLACEMENT STATUS (YES /NO) | NOC Issued Date | NOC Status (Pending by Faculty, Pending By TPO, Issued, Rejected) | Completion Letter (link)
1 | FINAL PLACEMENT 26-27 | 26-27 | 3001/INT/2026/00033 | 20205000301245 | BHOOMI K PARMAR | COT | B.TECH | CE | 7 | 7878787878 | BHM@GMAIL.COM | TCS | DEVELOPER | 3K | 2025-12-12 | 2026-01-12 | University Placement Drive |  |  |  | GUNJAN | 9898989898 | GUNJAN@GMAIL.COM | HR |  | YES | 2026-01-12 | Issued
2 | FINAL PLACEMENT 26-27 | 26-27 | 3001/INT/2026/00012 | 20205000302234 | RAJ SHARMA | COT | B.TECH | IT | 6 | 7878787878 | RAJ@GMAIL.COM | TATA | DEVELOPER | 10K | 2026-12-12 | 2027-01-30 | Self-Sourced/Off-Campus |  |  |  | RAJENDRA | 7889787978 | RAJENDRA@GMAIL.COM | HR |  | N0 | 2026-01-22 | Issued
NO - DUE DATA COUNT REPORT
Sr | Passing Year (Added By Student In No-Due Form) | INSTITUTE/COLLEGE | PROGRAM/COURSE | BRANCH/SPECIALIZATION | SEM/YEAR | TOTAL NO OF STUDENTS | NO DUE COUNT | Job / Employment | Business / Entrepreneurship | Planning for Further Studies | Admission Taken for Further Studies | Competitive Exam Preparation
1 | 2026 | COT | M.TEHC | ME | 5 | 1500 | 1000 | 100 | 200 | 100 | 0 | 100
2 | 2026 | COT | M.TEHC | IT | 4 | 1000 | 800 | 100 | 200 | 100 | 0 | 100
NO - DUE DATA LISTING & EXPORT REPORT
Sr | Passing Year (Added By Student In No-Due Form) | ENROLLMENT NO | STUDENT NAME | INSTITUTE/COLLEGE | PROGRAM/COURSE | BRANCH/SPECIALIZATION | SEM/YEAR | CONTACT NO | EMAIL ID | NO DUE TYPE (Job / Employment, Business / Entrepreneurship, Planning for Further Studies, Admission taken for further Study, Competitive Exam Preparation) | UPLOADED DOCUMENT LINK | Student Photo (link) | Admission Year | Batch | No Due Date (Record Added Timestamp)
1 | 2026 | 20205000301245 | BHOOMI K PARMAR | COT | B.TECH | CE | 7 | 9898989898 | BHM@GMAIL.COM | Job / Employment |  |  | 24 | 24-27 | 2026-12-12
2 | 2026 | 20205000302234 | RAJ SHARMA | COT | B.TECH | IT | 6 | 7878787878 | RAJ@GMAIL.COM | Admission taken for further Study |  |  | 24 | 24-27 | 2026-12-22
COMPANY DATA COUNT REPORT 1
Sr | POSTING TYPE (Muplti Selection) | TOTAL COMPANIES | TOTAL APPLICATIONS COUNT | APPLICATIONS OFFER RELESED COUNT | HIGHEST COMPANY PACKAGE RANGE | LOWEST COMPANY PACKAGE RANGE
1 | FINAL PLACEMENT 26-27 | 1500 | 1000 | 500 | 7-8 LPA | 2-3 LPA
2 | FINAL PLACEMENT 26-27 | 2000 | 1000 | 800 | 8 - 9 LPA | 4 - 5 LPA
COMPANY DATA COUNT REPORT 2
Sr | POSTING TYPE (Muplti Selection) | TOTAL COMPANIES | TOTAL APPLICATIONS COUNT | APPLIED STUDENTS COUNT | MOCK ROUND STUDENTS COUNT | SHORTLISTED STUDENTS COUNT | TEST SCHEDULED STUDENTS COUNT | INTERVIEW STUDENTS COUNT | HR ROUND STUDENTS COUNT | OFFER REALSED STUDENTS COUNT | REJECTED STUDENTS COUNT
1 | FINAL PLACEMENT 26-27 | 1500 | 1000 | 1000 | 2 | 3 | 4 | 5 | 6 | 7 | 8
2 | FINAL PLACEMENT 26-27 | 2000 | 1000 | 800 | 2 | 3 | 4 | 5 | 6 | 7 | 8

## EXISTING REPORTS REMARK
Student Management
Interested Students | REMOVE
Eligibility Report | LOOK LIKIE PROFILE COMPLITION DESIGN (Remove Student wise listing and add deparment wise graph)
change title from roll number to enrollment number in export csv
Profile Completion | change title from roll number to enrollment number in export csv
Roll Number shows null issue
Registration Summary | REPLACE PROGRAM TYPE WITH POSTING TYPE, also check export data
Employer Management
Company Master List | REMOVE
Recruiter List | REMOVE
Engagement History | REMOVE
Company Classification | REMOVE
Job & Internship Postings
Active Postings | REMOVE
Posting History by Year | REMOVE YEARS BOXES, Not remove filter year dropdown
Posting type wise DATA IS NOT LISTED (Issue)
Internship vs Placement | REMOVE
Events & Campus Drives
Event-wise Attendance | REMOVE
Drive Completion Summary | REMOVE
Student Participation History | Remove print and pdf option & All Branch dropdown
add institute, course, branch
change title from roll number to enrollment number in export csv
NOC & Documents
Pending NOC Requests | REMOVE
Issued NOC Register | REMOVE
NOC by Department / Batch | REPLACE ALL TYPE DROPDOWN FILTER WITH POSTING TYPE
Remove print and pdf option
Applications & ATS
Applicant List per Opportunity | REMOVE
Stage-wise Application Count | Remove print and pdf option
Shortlist vs Rejection | Remove print and pdf option
Remove All Deparment dropdown
Offers & Joining
Offer Acceptance Summary | Remove print and pdf option
Remove All Deparment dropdown
Joining Status Summary | REMOVE
Active Offer Compliance | REMOVE
Internships & Stipends
Internship Status Summary | REMOVE
Certificate Pending | REMOVE
Company-wise Summary | REMOVE
Portfolio & Showcase
Portfolio Completion | REMOVE
Published Portfolios | REMOVE
Communication
Announcement History | REMOVE
Consent Tracking | REMOVE
Placement Analytics
Placement Cell Report | REMOVE
Placement Summary | REMOVE
Company Performance | REMOVE
Offer-to-Join Funnel | REMOVE
Unplaced Students | Remove All Deparment dropdown
add institute, course, branch
Listing and export data remove deparment and add institute, course, branch, semester

## ENHANCEMENTS
SR | POINTS | TYPE | STATUS | REMARKS | Heptanesia Remarks | Live Status
1 | Bug Title : Approval Should Be Mandatory Before Adding a Student to Any Program /Posting type & Withdrawl Option Required From TPO Admin | Enhancement | UAT
2 | Requirement: Add an Export to CSV option in the Event Records module to download the attendance records of an event. | Enhancement
3 | Title: Rename "Assigned University Drive" to "Released Offers by TPO" Requirement: Change the label "Assigned University Drive" to "Released Offers by TPO" in the NOC Request module. The dropdown should display all offers that have been marked as Released Offer in the Campus Drives module. Ensure the data mapping and synchronization are working correctly so that all released offers are available for selection. | Enhancement | UAT | Accepted |  | Done
4 | Bug Title: Posting Type Filter Missing & Search Box Auto-Deselect Issue in Posting Operations Description: 1.Missing Posting Type Filter In the Posting Operations module, there should be a Posting Type filter to allow users to filter records based on the selected posting type. 2.Search Box Auto-Deselects In the Search box of Posting Operations, after entering a single character, the search field automatically loses focus (gets deselected), preventing continuous typing. Expected Result: A Posting Type filter should be available in Posting Operations. The search box should remain focused while typing and should not automatically deselect after entering a character. Actual Result: Posting Type filter is not available. Search box loses focus automatically after typing the first character. | Bug/Enhancement | UAT | Accepted |  | Done
5 | Enhancement Requirement: Module: TPO Admin → Master → Posting Types Please add an Application Receiving ON/OFF toggle above the Edit / Deactivate / Delete buttons. When Application Receiving is set to OFF, the corresponding Posting Type should still be visible on the Student Dashboard, but the Register button under Interest Registration should be disabled. Students should not be able to enroll/apply for that posting type until Application Receiving is turned ON again. All other functionalities should remain unchanged. | Enhancement | UAT
6 | Title: Posting Type Configuration – Add Toggle for Mandatory Internship Completion Certificate Submission Requirement: While creating a Posting Type, add a toggle option: Toggle Name: This Program Requires Internship Completion Certificate Default Value: OFF When the toggle is ON, students who receive an Internship NOC under that Posting Type must upload their Internship Completion Certificate/Completion Letter issued by the company. Once the NOC duration ends, the system should automatically enable the document upload option for the student. Students must upload the Internship Completion Certificate/Letter within 15 days from the Internship/NOC end date. The uploaded document should be available for verification by the Training & Placement Cell. Until the document is uploaded (or the 15-day window expires), the internship status should remain "Completion Certificate Pending." After verification by the T&P Cell, the status should be updated to "Internship Completed." Acceptance Criteria: A new toggle is available while creating/editing a Posting Type. If the toggle is OFF, no completion certificate upload is required. If the toggle is ON, the student is prompted to upload the completion certificate after the NOC end date. The upload window remains open for 15 days from the internship end date. Students can upload their Internship Completion Certificate in the "Past NOC Requests" section after completing their internship. The T&P Cell can view, verify, approve, or reject the uploaded certificate. Student and T&P dashboards display the current completion certificate status (Pending, Uploaded, Approved, Rejected, Expired). The system should send automated reminders to students until the certificate is uploaded or the 15-day deadline is reached. | Enhancement
7 | Bug Title: Validation Field Does Not Redirect to the Relevant Section Description: When a validation error occurs, clicking on the validation message or attempting to submit the form does not redirect the user to the respective field containing the error. The system should automatically navigate to and focus on the first validation field that requires correction, allowing users to identify and resolve the issue easily. | Enhancement | UAT
8 | Title: Email Validation Should Accept Both Domains Description: The email validation should accept users with both @socet.edu.in and @silveroakuni.ac.in email domains. Expected Result: The system should allow email IDs ending with @socet.edu.in and @silveroakuni.ac.in. Actual Result: Only one domain is accepted during validation. | Enhancement | UAT
9 | Title: Password validation needs to be updated. Expected Validation: Minimum 8 characters. Must contain at least one uppercase letter (A–Z). Must contain at least one special character (e.g., @, #, $, %, &, *). The current validation of only 8 characters should be replaced with these stronger password | Enhancement | UAT
10 | Bug Description: No Due Approval Validation Missing Once a student's No Due request has been approved, the No Due process for that student is considered complete. Expected Result: After a student's No Due request is approved: The student should not be able to submit another No Due request. The TPO Admin should not be able to approve any previously rejected or pending No Due requests for that student. All actions related to the No Due process should be disabled, ensuring that only one approved No Due record exists for each student. | Validation | UAT
11 | Once a student's No Due request has been approved, the student's placement and internship process is considered closed. Expected Behavior: Only one No Due request should be allowed per student. After the No Due request is approved, the student should not be able to: Apply to any new Posting type/ Posting Generate or request a new NOC. Access or use any placement or internship-related services. All placement and internship-related actions should be automatically disabled after No Due approval. | Validation | UAT
12 | Bug:Apply Button Should Be Disabled After Offer Release Under same Posting Type(Program) Expected Result:Once a student's offer has been released for a company under a specific Posting Type, the Apply button should be disabled for all other company openings under the same Posting Type. Actual Result: The Apply button remains enabled, allowing the student to apply to other companies under the same Posting Type even after an offer has been released. | Validation
13 | ADD SECTOR DROPDOWN FILTER POSTING -JOB& INTERNSHIP POSTING : https://placementcrm.silveroakuni.ac.in/admin/postings | Enhancement Request
14 | REPLACE ALL TYPE DROPDOWN WITH POSTING TYPE DROPDOWN FILTER ( Each Case) | Enhancement Request | UAT
15 | NOC Request (student) : In the Self-Sourced/Off-Campus Company Name search field, add an "Other – Enter New Company" option at the top of the search results, allowing users to add a new company if it is not available in the existing list. | Enhancement Request | UAT
16 | Add a "Pending Faculty" dashboard card (Summary Counter) in the NOC Management summary section. | Enhancement Request | UAT
17 | Student Login: NOC Apply Form: Add an Internship Type Check Box after the Start Date and End Date fields with the following options: Value: Internship + Placement | Enhancement Request | UAT
18 | Enhancement: TPO Admin → Applications → Application Pipeline In the student list displayed under the Application Pipeline, add a Resume column with a "View Resume" link. It should open the same resume submitted by the student while applying for that specific job/posting. | Enhancement Request
19 | TPO Admin -> Offer & Joining Management → Create Offer Add a Posting Type dropdown filter at the top of the Create Offer page. This will allow users to select the relevant posting type before creating an offer, ensuring that only the corresponding job postings and eligible student data are displayed. | Enhancement Request
20 | Enhancement Request Module: TPO Admin → Toggle Sidebar → Events & Drives → Create Event Requirement: Add a Stage dropdown below the Linked Postings (Roles) field. Based on the selected stage, the Target Audience should be filtered automatically. Stage Dropdown Options: All Applied Mock Round Shortlisted Test Scheduled Interview HR Round Offer Released Rejected | Enhancement Request
21 | TPO Admin Dashboard: Display only the 10 most recent Interest Registration records on the dashboard; all older records should be accessible from the Generate List/View All page. | Enhancement Request

## OLD UAT
SR | POINTS | TYPE | STATUS | REMARKS
1 | Policy Creation select the Posting type. But keep the other selecltions of University etc. | Enhancement | UAT | Accepted
2 | During registration by Student, the policy needs to be popped up and only when student accepts he is registered. | Enhancement | UAT | Accepted
3 | Where a policy is not linked to a posting type, it should be shown in profile and accepted. | Enhancement | UAT | not working - pending , heptanesia - check my profile there is tab called policies
4 | Policies linked to postings will anyway be shown in dashboard. | Information | Pending
5 | Student Profile - Showing of skills - wrap. (with show more and less). | Enhancement | UAT | Accepted
6 | Skills (Master and Selection TBD). | Information | Pending
7 | Student Profile - Projects - Git hub and Demo URL as Non Mandatory. | Enhancement | UAT | Accepted
8 | Make list of Job Types - Fulltime, Parttime. | Enhancement | UAT | Accepted
9 | Employement section, remove duration, allow multiple and during close, upload document (mandatory). | Enhancement | UAT | Accepted
10 | Not interested in placement (capture reason). Have a tab in Profile. Confirm and then lock. - For posting types have toggle. Show but do not allow register. | Enhancement | UAT | Pending: Interested in placement : Reopen by TPO admin only, heptanesia - fixed
11 | History of enable or disable. | Enhancement | UAT | Pendiing : not able to find history , heptanesia - fixed
12 | My Portfolio - Projects and Internship. Remove settings tab. Move Portfolio Summary - On top. | Enhancement | UAT | Accepted
13 | View as recruiters. - remove view as recruiter toggle. | Enhancement | UAT | Accepted
14 | Offer letters not to be shown for Recruiters | Information | UAT | Unable to load recruiter dashboard
15 | Offer letter and completion certificate mandatory. | Enhancement | UAT | Accepted
16 | Below Logout, Take change password option. | Enhancement | UAT | Accepted
17 | Other user profile pages (TPO Admin, Admin etc.) | Bug | UAT | Accepted
18 | Give Academic Year for Posting Types and give filter for Academic Year wise. | Enhancement | UAT | Accepted
19 | Confirmation Dialog for all delete. | Enhancement | UAT | Accepted
20 | Student Management - Verification/All - Show filter of Posting types, and show the posting types in the list of Verifications. and all other Tabs. | Enhancement | UAT | Accepted
21 | Student Details - Show Employment details. | Enhancement | UAT | Accepted
22 | Student Management - Selection Database. Filter based only on Posting types. | Enhancement | UAT | Filter not working - fixed
23 | Notifications. | Bug | UAT | Not working
24 | Student Management - All Students - Date wise. and Increase records per page to 100. | Enhancement | UAT | Accepted
25 | Add Company - Put Star everywhere. Make website optional. remove http / https mandatory check. | Enhancement | UAT | Accepted
26 | Remove verificaiton of Recruiter if TPO admin is creating. | Enhancement | UAT | Accepted
27 | Request of NOC show posting types where applied. | Enhancement | UAT | Accepted
28 | NOC - Drop downs for Name, State, City, Position with Other, Pan and GST, Upload supporting documents. | Enhancement | UAT | City Drop downs not working , heptanesia: city to be typed
29 | Company Verified when NOC is verified. Company is Marked as from Student. | Enhancement | UAT | Pending, not showing tag of company added by students
30 | Create user when Recruiter is created. | Enhancement | UAT | Accepted
31 | Super admin can activate or deactivate the Recrutier. On Activation password is sent. | Enhancement | UAT | Accepted
32 | Posting Types should have list of companies, that have been on that type so far. | Enhancement | UAT | Accepted
33 | Recruiter - None of the screens are loading. | Bug | UAT | Accepted
34 | Resume Manager, Allow only PDF | Enhancement | UAT | Accepted
35 | Top left side logo to keep in full view (remove text SOU). Add user type chip below or on the right topside near the logout button | Enhancement | UAT | Accepted
36 | Change Favicon remove Lovable icon and replace it with SOU icon. | Enhancement | UAT | Accepted
37 | Create user - Remove Student. | Enhancement | UAT | Accepted
38 | Show where NOC is (Even if it is at Faculty Coordinator), else TPO admin only sees it when faculty coordinator approved. | Enhancement | UAT | Accepted
39 | Close Dialog on Cross only, If i click externally it goes away and data gets blank. | Bug | UAT | Accepted
40 | Send parameters to list students - based on Institute, Branch or Semester (Make all conditions OR) Option: Student Directory in Faculty Coordinator. | Bug | UAT | Issue Observed: In the Faculty Coordinator module, all students are not visible in the Student Directory. Also, the Institute and Semester dropdown options are not loading. heptanesia :fixed
41 | Student Directory - Not shown for Faculty Coordinator. | Bug | UAT | Accepted with Issue Observed
42 | Remove TPO Employee from List of users in create user. | Enhancement | UAT | Accepted
43 | Deselect Institute - Not working in Create User. | Bug | UAT | Accepted
44 | Remove SuperAdmin option from Create User. | Enhancement | UAT | Accepted
45 | All TPO, Management and Facutly email ID to be from silveroak.ac.in | Enhancement | UAT | Use: silveroakuni.ac.in
46 | Management screen is completely blank. | Bug | UAT | Fixed to show profile as of now we need to discuss what to show.
47 | Postings - Remove Application Override. | Enhancement | UAT | Accepted
48 | Job Description PDF to be Multiple. | Enhancement | UAT | Pending : Don't PDF Renamed with pdf 1, pdf 2 etc keep name as it is , heptanesia: fiixed
49 | Posting type instead of Student Visibility. | Enhancement | UAT | Accepted
50 | Posting Location (City). / Multiple Location select. | Enhancement | UAT | Accepted
51 | Range of Salary/Stipend in the Job Posting. | Enhancement | UAT | Pending : give option to add range not option to select range , heptanesia : fixed
52 | Appropriate - Error and then Highlight. In all Modules. | Bug | UAT | pending, only showing error but not redirecting to where is error
53 | Create and add Another. In Postings - Remove. | Enhancement | UAT | Accepted
54 | Postings not clearly visible. - Selected branches | Bug | UAT | Accepted
55 | CGPA mismatch of NULL and zero. | Bug | UAT | Accepted
56 | Application management, filter not working when we select a particular post | Bug | UAT | Filter not working
57 | Application Profile - Application Records Rename student tab to Profile | Enhancement | UAT | Accepted
58 | Student should be blocked in a posting type only when Offer is released. Not before that. | Bug | UAT | Accepted
59 | Block even when there is self placed NOC for the same Posting Type | Enhancement | UAT | Pending NOC Is not showing faculty coordinator for verification
60 | Create offer (cannort read properties of).trim | Bug | UAT | Accepted
61 | Once offer is released show for acceptance. | Bug | UAT | Accepted
62 | Show posting types in the list of My Applications in Student | Enhancement | UAT | Accepted
63 | NOC Type to be removed from Create NOC | Enhancement | UAT | Accepted
64 | Remove Mandatory for end date in Create NOC | Enhancement | UAT | Accepted
65 | Reference number generation in NOC PDF | Bug | UAT | SOU/TPO/MM-YYYY/TYP/0001 not working properly
66 | Display Company proof, document uploaded in NOC pdf Approval. (TPO admin) | Enhancement | UAT | Pending not showing because of noc is pending at faculty coordinator
67 | NOC Approval is not happening in Approve and Issue of TPO admin | Bug | UAT | NOC is still not visible to assigned faculty coordinators/ still not working at approval time\
68 | Noc Template remove Mobile Number. | Enhancement | UAT | Pending. Heptanesia Reply: It will only happen in new PDFs old will still show. SOU Reply: NOC issue is not working so pending, not able to approve NOC by TPO
69 | Reference Number in NOC take 3 char of posting type SOU/TPO/MM-YYYY/XXX/NNNN | Bug | UAT | SOU/TPO/MM-YYYY/TYP/0001 (MM-YYYY not fatching)
70 | Event Type masters to be created | Enhancement | UAT | Accepted
71 | Select Pipleline stages in the Create event to send to the particular pipeline only | Enhancement | UAT | Pending not showing option for select particular status students
72 | Put attachment in Announcement PDF and Image | Enhancement | UAT | Accepted
73 | Create Announcement - Remove batch from dropdown, add semester, remove checkbox of department | Enhancement | UAT | Accepted
74 | Event not being shown in Circular | Bug | UAT | Events not Fatching , heptanesia : only event with status published will be fetched
75 | Circular Not seen in Student (No menu and not in Dashboard) | Bug | UAT | Accepted
76 | Student Dashboard - Dot in new (read and unread) | Enhancement | UAT | Not working
77 | Issue NDC not required in No Dues Approval | Enhancement | UAT | Accepted
78 | No Dues List Export All details and Offer letter Attachment | Enhancement | UAT | Accepted
79 | Add New Policy Document - Category option to be add for all students and also shown while student registration process | Enhancement | UAT | Accepted
80 | TPO Admin:- When a student shows interest in any program, all relevant details must be updated and maintained in the Interest Lists section available at: https://silveroak.heptanesia.com/admin/interests Additionally, the Excel Export should contain complete student information, including academic details such as Institute, Branch, Course, Semester, and other relevant fields, as these details are required for departmental reporting. Since the list of students registered for a program needs to be shared with the respective departments, it is essential that all necessary student information is available in the export file for seamless data sharing and record management. | Enhancement
81 | Faculty Coordinators :- Note: Faculty Coordinators should be able to view their assigned programs along with the students who have enrolled or shown interest in them. They should also be able to view the complete batch-wise student list, including students from programs not assigned to them. Additionally, the Posting Type/Program in which a student's offer has been released should be visible, and students who have applied for and received a NOC should be clearly marked in the list. | Enhancement
82 | TPO Admin:- In the Pending Verification section, the Posting Type (Program Name) label is visible; however, the actual Posting Type/Program data is not being linked or fetched correctly. As a result, it is not possible to identify which program the student has enrolled in or shown interest in. The Posting Type should be properly mapped and displayed so that the concerned Faculty Coordinators and the Training & Placement Cell can verify the student's application efficiently. | Bug
83 | In Super Admin → Security & Access Control, under the "All Users" text box, users are getting automatically deselected after entering a single character. | Bug
84 | Offers marked as "Released Offer" in the Campus Drives module are not appearing under Placement Source → University Placement Drive → Assigned University Drive during NOC Request submission; please verify the mapping and data synchronization. | Bug
85 | Every where Excel Export should include complete details such as Student Name, Enrollment Number, Institute, Branch, Course, Semester, and other relevant academic information, as these records are required to be shared with the respective Academic Heads for filing and documentation purposes.EVve | Enhancement
86 | Company Change NOC – Functional Flow Required Changes in NOC Apply Screen Option 1: Apply for Fresh NOC Option 2: Apply for Company Change NOC Student selects Apply for Company Change NOC. Student enters the following details: Old NOC Number (Mandatory) Reason for Company Change (Mandatory) Student uploads the required documents: Termination Letter/Relieving letter from the old company (Mandatory) Offer Letter from the new company (Mandatory) The request is sent to the Faculty Coordinator and TPO Admin for approval. After approval: The Old NOC is marked as Void/Closed. A New NOC is generated for the new company under the same running Internship/Program. The student continues the remaining duration of the program with the new company. Company Change NOC option should be available only if: The previous NOC exists. The Internship/Program is still active. | Enhancement
87 | Please add an Application Receiving ON/OFF toggle above the Edit / Deactivate / Delete buttons. When Application Receiving is turned OFF, no new student applications should be accepted and the Apply button should be disabled. Existing applications and the program status should remain unaffected. | Enhancement